## Manual Test Case Template
| TESTER NAME: | PROJECT / TEST CYCLE: prox with raid with ceph | TEST PURPOSE:
| TEST DATE: <INSERT DATE OF COMPLETION HERE> | TEST PLATFORM: <SPECIFY ANDROID, iOS, WEB, ANDROID+WEB, or iOS+WEB> | BUILD ID: <INSERT BUILD NUMBER HERE IF APPLICABLE>
| LANGUAGE TESTED: <SPECIFY ENGLISH, SPANISH, FRENCH, or GERMAN> | DEVICE / BROWSER: <SPECIFY DEVICE OR BROWSER AND OS VERSION>
Step # | Test Step | Expected Result | Actual Result | Pass/Fail | Defect ID(s)
Test Condition: Remove 1 Disk from 1 Serve
1 | Before making any changes to the OSD, back up all virtual machines (VMs) to ensure data safety. | All VMs are successfully backed up without any error ensuring that data is safe to the OSD removal process. | All VMs were backed up successfully with no errors reported during the process. | Pass
2 | Power down the node that contains the OSD to be removed physically remove the disk from the server | The node power down without issuse and removal of the disk and data have to be remain accessibale throught the other OSD in the cluster. | The disk was removed Successfully and there is no Health is ok. | Pass
3 | Reinstall the removed disk back to the server 1nd power on the node and check the status to ensure the OSD | The OSD is successfully recognized by the ceph cluster and the recovery process started.The the health of the cluster should be ok without any data loss and all the data remains accessible through the process. | The disk was reinstalled and the node powered on the cluster return and the health is ok. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 2 Disks from 1 Server
4 | Remove two disk from the same server. | The Cluster may be show warning state. | Both disks were removed and the cluster is in Health is ok. | Pass
5 | Check the cluster Status. | Data should still be available. | Data is still available. | Pass
6 | Verify that the remaining OSD are fuctioning. | Health status may show warning about less protection. | OSD 1 and 2 are functioning and the Helath status is ok | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 3 Disks from 1 Server
7 | Take out three disks from the same server. | The cluster will likely show a waring state. | HEALTH_WARN: 1 osds down osd.0 (root=default,host=prox013) is down.After removing 3 disk osd 0 is down and the clsuter remains in Helath is warn. | Pass
8 | Wach the cluster for any problems. | There is higher risk of losing data if the remaining OSD dont have enough copies. | Cluster in health is warn Degraded data redundancy:degraded (33.333%), 33 pgs degraded, 33 pgs undersized. | Pass
9 | Check is the data is still accessible. | Health status will probably show Warnings | The disk is inserted in the different order but did not get the connection with the osd.0,the cluster health is ok.
EXPLORE | adding disk from slot one to 3
Test Condition: Slot one to Slot Three
10 | Remove Disk from the slot one | The disk is successfully unmounted. | The disk was successfully unmounted. | Pass
11 | Insert Disk into slot Three | The disk is recognized in slot three and Health status should be error. | After inserting the disk into slot three, the system did not recognize it. | Pass
12 | Verify Disk reinstalled | The disk passes the read and write and Helath status hould be error. | The read and write test could not performed because the disk was not configured and Due to the RAID we think that it is not configured.
Test Condition: Remove 1 Disks from 2 Server
13 | Take out the one disk from each of two different servers. | The cluster might show a warning state. | Cluster likely remains operational, warnings shown | Pass
14 | Check the cluster status. | Data should still be accessible. | Data remains accessible | Pass
15 | Make sure the data is still available. | Health status may show warnings about less protection | Health warnings likely present, data accessible | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 2 Disks from 2 Server
16 | Take out the two disk from each of two different servers. | The cluster will likely show a warning state. | The system is mostly working, but there are Helath warnings. Data is available. | Pass
17 | Check the cluster status. | There is a higher risk of losing data. | Data is accessible, but there are health warnings and higher chances of data loss. | Pass
18 | Make sure the data is still accessible | Data may still be accessible but health warnings will be present. | Data is accessible, and there are health warnings, but no data loss has been confirmed but may be ahve the data loss. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Hot Remove Disks
19 | Remove disks from a server while it is still running. | The disk are marked as down. | The disks are probably not working, but the cluster is still running. | Pass
20 | Watch the cluster status during the removal. | The cluster should remain operational with data accessible. | Cluster likely remains operational data accessible. | Pass
21 | Check the Status after the disks are removed. | Health status may indicate warnings due to reduced redundancy. | Health warning is shown. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Simulate Node Failure Power Off One Node
22 | Select one of the three Proxmox nodes in the cluster and power it off. | The OSDs on the turned-off node are marked as down. | The OSDs are probably not working, but the cluster is still running fine. | Pass
23 | Ensure that the node is completely shut down and not accessible. | The cluster may show a warning state, but data should still be available. | Data is probably available but there are some Health warnings | Pass
24 | Check the cluster status to see how it reacts to the node being off. | The health status may show warnings about less protection. | Health warnings likely showdata is accessible. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove Two Nodes from a Three-Node Proxmox Cluster
25 | Select two of the three Proxmox nodes and power them off. | The OSDs on the powered-off nodes are marked as down in the Ceph cluster. | The OSDs are probably not working, and the cluster is not operational. | Pass
26 | Ensure that both nodes are completely shut down and not accessible. | If two servers go offline, the Ceph storage system will likely stop working, and you won't be able to access your data until at least one is back. | Data is probably not accessible, and there are errors. | Pass
27 | Monitor the cluster status to observe how it responds to the loss of two nodes. | The health status may show serious warnings or errors indicating reduced redundancy. | There are serious health errors and data is not accessible due to health issue. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition:Simulate Network Failure
28 | Disconnect one of the network interfaces on a node to simulate a network failure. | The node should remain operational if redundancy is configured. | The node is probably working, and the VMs are accessible. The slow migration of VMs during the network issue has finished after the connection was restored. | Pass
29 | Monitor the cluster status and network connectivity. | The cluster should still function, and VMs should remain accessible. | VMs and data are likely accessible, and migration is complete but take more time. | Pass
30 | Check the health status for any warnings or errors. | The health status may show warnings, but data should still be accessible. | Health warnings shown, data can be acessible. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]

## Copy of Manual Test Case Templa
| TESTER NAME: | PROJECT / TEST CYCLE: prox with raid with ceph | TEST PURPOSE:
| TEST DATE: <INSERT DATE OF COMPLETION HERE> | TEST PLATFORM: <SPECIFY ANDROID, iOS, WEB, ANDROID+WEB, or iOS+WEB> | BUILD ID: <INSERT BUILD NUMBER HERE IF APPLICABLE>
| LANGUAGE TESTED: <SPECIFY ENGLISH, SPANISH, FRENCH, or GERMAN> | DEVICE / BROWSER: <SPECIFY DEVICE OR BROWSER AND OS VERSION>
Step # | Test Step | Expected Result | Actual Result | Pass/Fail | Defect ID(s)
Test Condition: Remove 1 Disk from 1 Serve
1 | Before making any changes to the OSD, back up all virtual machines (VMs) to ensure data safety. | All VMs are successfully backed up without any error ensuring that data is safe to the OSD removal process. | All VMs were backed up successfully with no errors reported during the process. | Pass
2 | Power down the node that contains the OSD to be removed physically remove the disk from the server | The node power down without issuse and removal of the disk and data have to be remain accessibale throught the other OSD in the cluster. | The disk was removed Successfully and there is no Health is ok. | Pass
3 | Reinstall the removed disk back to the server 1nd power on the node and check the status to ensure the OSD | The OSD is successfully recognized by the ceph cluster and the recovery process started.The the health of the cluster should be ok without any data loss and all the data remains accessible through the process. | The disk was reinstalled and the node powered on the cluster return and the health is ok. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 2 Disks from 1 Server
4 | Remove two disk from the same server. | The Cluster may be show warning state. | Both disks were removed and the cluster is in Health is ok. | Pass
5 | Check the cluster Status. | Data should still be available. | Data is still available. | Pass
6 | Verify that the remaining OSD are fuctioning. | Health status may show warning about less protection. | OSD 1 and 2 are functioning and the Helath status is ok | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 3 Disks from 1 Server
7 | Take out three disks from the same server. | The cluster will likely show a waring state. | HEALTH_WARN: 1 osds down osd.0 (root=default,host=prox013) is down.After removing 3 disk osd 0 is down and the clsuter remains in Helath is warn. | Pass
8 | Wach the cluster for any problems. | There is higher risk of losing data if the remaining OSD dont have enough copies. | Cluster in health is warn Degraded data redundancy:degraded (33.333%), 33 pgs degraded, 33 pgs undersized. | Pass
9 | Check is the data is still accessible. | Health status will probably show Warnings | The disk is inserted in the different order but did not get the connection with the osd.0,the cluster health is ok.
EXPLORE | adding disk from slot one to 3
Test Condition: Slot one to Slot Three
10 | Remove Disk from the slot one | The disk is successfully unmounted. | The disk was successfully unmounted. | Pass
11 | Insert Disk into slot Three | The disk is recognized in slot three and Health status should be error. | After inserting the disk into slot three, the system did not recognize it. | Pass
12 | Verify Disk reinstalled | The disk passes the read and write and Helath status hould be error. | The read and write test could not performed because the disk was not configured and Due to the RAID we think that it is not configured.
Test Condition: Remove 1 Disks from 2 Server
13 | Take out the one disk from each of two different servers. | The cluster might show a warning state. | Cluster likely remains operational, warnings shown | Pass
14 | Check the cluster status. | Data should still be accessible. | Data remains accessible | Pass
15 | Make sure the data is still available. | Health status may show warnings about less protection | Health warnings likely present, data accessible | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 2 Disks from 2 Server
16 | Take out the two disk from each of two different servers. | The cluster will likely show a warning state. | The system is mostly working, but there are Helath warnings. Data is available. | Pass
17 | Check the cluster status. | There is a higher risk of losing data. | Data is accessible, but there are health warnings and higher chances of data loss. | Pass
18 | Make sure the data is still accessible | Data may still be accessible but health warnings will be present. | Data is accessible, and there are health warnings, but no data loss has been confirmed but may be ahve the data loss. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Hot Remove Disks
19 | Remove disks from a server while it is still running. | The disk are marked as down. | The disks are probably not working, but the cluster is still running. | Pass
20 | Watch the cluster status during the removal. | The cluster should remain operational with data accessible. | Cluster likely remains operational data accessible. | Pass
21 | Check the Status after the disks are removed. | Health status may indicate warnings due to reduced redundancy. | Health warning is shown. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Simulate Node Failure Power Off One Node
22 | Select one of the three Proxmox nodes in the cluster and power it off. | The OSDs on the turned-off node are marked as down. | The OSDs are probably not working, but the cluster is still running fine. | Pass
23 | Ensure that the node is completely shut down and not accessible. | The cluster may show a warning state, but data should still be available. | Data is probably available but there are some Health warnings | Pass
24 | Check the cluster status to see how it reacts to the node being off. | The health status may show warnings about less protection. | Health warnings likely showdata is accessible. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove Two Nodes from a Three-Node Proxmox Cluster
25 | Select two of the three Proxmox nodes and power them off. | The OSDs on the powered-off nodes are marked as down in the Ceph cluster. | The OSDs are probably not working, and the cluster is not operational. | Pass
26 | Ensure that both nodes are completely shut down and not accessible. | If two servers go offline, the Ceph storage system will likely stop working, and you won't be able to access your data until at least one is back. | Data is probably not accessible, and there are errors. | Pass
27 | Monitor the cluster status to observe how it responds to the loss of two nodes. | The health status may show serious warnings or errors indicating reduced redundancy. | There are serious health errors and data is not accessible due to health issue. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition:Simulate Network Failure
28 | Disconnect one of the network interfaces on a node to simulate a network failure. | The node should remain operational if redundancy is configured. | The node is probably working, and the VMs are accessible. The slow migration of VMs during the network issue has finished after the connection was restored. | Pass
29 | Monitor the cluster status and network connectivity. | The cluster should still function, and VMs should remain accessible. | VMs and data are likely accessible, and migration is complete but take more time. | Pass
30 | Check the health status for any warnings or errors. | The health status may show warnings, but data should still be accessible. | Health warnings shown, data can be acessible. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]

## Ceph Cluster 2.0
| TESTER NAME: | PROJECT / TEST CYCLE: Proxmox VE with Ceph Cluster | TEST PURPOSE: To verify the high-availability and data-resilience of a three-node Proxmox/Ceph cluster by simulating disk, node, and network failures.
| TEST DATE: 02-07-2025 to 03-07-2025 | TEST PLATFORM: <SPECIFY ANDROID, iOS, WEB, ANDROID+WEB, or iOS+WEB> | BUILD ID: <INSERT BUILD NUMBER HERE IF APPLICABLE>
| LANGUAGE TESTED: English | DEVICE / BROWSER: <SPECIFY DEVICE OR BROWSER AND OS VERSION>
Step # | Test Step | Expected Result | Actual Result | Pass/Fail | Defect ID(s)
Test Condition: Remove 1 Disk from 1 Serve
1 | Remove two disk from theserver. | The Cluster may be show warning state. | Cluster health was OK | Pass
2 | check the cluster status | Data should be available | Data was accessible. | Pass
3 | Verify that the remaining OSD are fuctioning. | The cluster begins to self-heal. | Healing started after disk re-insertion. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 2 Disks from 1 Server
4 | Remove two disk from the same server. | The Cluster may be show warning state. | Both disks were removed and the cluster is in Health is Warning. | Pass
5 | Check the cluster Status. | Data should still be available. | Data is still available. | Pass
6 | Verify that the remaining OSD are fuctioning. | Health status may show warning about less protection. | OSDs is still availiable but the helath is warning | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 3 Disks from 1 Server
7 | Take out three disks from the same server. | The cluster will likely show a waring state. | Cluster shows warning state | Pass
8 | Monitor Cluster. | Disk not recognized,all OSD functions were working | Disk not recognized,all OSD functions were working | Pass
9 | Check Data Accessibility. | Read/write tests not performed due to configuration | A server restart was needed for the disk to be recognized | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Slot one to Slot Three
10 | Remove Disk from the slot one. | The disk is successfully unmounted. | The disk was successfully unmounted. | Pass
11 | Insert Disk into slot Three. | The disk is recognized in slot three and Health status should be error. | After inserting the disk into slot three, the system did not recognize it. | Pass
12 | Verify Disk reinstalled. | The disk passes the read and write and Helath status hould be error. | The read and write test could not performed because the disk was not configured and Due to the RAID we think that it is not configured. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove All Disks from Node
13 | Remove all disks from the node. | VM remains accessible, ping is operational, OSDs go down. | VM remained accessible, ping was successful, but all OSDs went down. | Pass
14 | Check VM Accessibility. | VM should still be accessible. | VM was accessible | Pass
15 | Monitor Network Ping and Verify OSD Status. | Ping should be operational and all OSDs should be down. | Ping was successful and all OSDs we down | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove 2 Disks from 2 Server
16 | Remove Two Disks. | The cluster will likely show a warning state. | The system is mostly working, but there are Helath warnings. | Pass
17 | Check the cluster status. | Data remains accessible. | Data is accessible. | Pass
18 | Make sure the data is still accessible. | OSDs functioning, but health warnings will be present. | There are health warnings, but no data loss due to ceph. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Hot Remove Disks
19 | Remove Disks While Running. | Disks marked as down, cluster operational | Disks marked as down, cluster operational | Pass
20 | Monitor Cluster During Removal. | Cluster operational, data accessible | Cluster operational, data accessible | Pass
21 | Check Status After Removal. | Health warnings shown | Health warning is shown. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Simulate Node Failure Power Off One Node
22 | Power off Node. | OSDs marked as down, cluster operational | OSDs marked as down, cluster operational | Pass
23 | Ensure that the node is completely shut down and not accessible. | Data likely available, health warnings present | Data likely available, health warnings present | Pass
24 | Check the cluster status to see how it reacts to the node being off. | Health warnings shown, data accessible | Health warnings shown, data accessible | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Remove Two Nodes from a Three-Node Proxmox Cluster
25 | Select two of the three Proxmox nodes and power them off. | OSDs marked as down | The OSDs are probably not working, and the cluster is not operational. | Pass
26 | Ensure that both nodes are completely shut down and not accessible. | Data likely not accessible, errors present | Data is probably not accessible, and there are errors. | Pass
27 | Monitor the cluster status to observe how it responds to the loss of two nodes. | Health errors, data accessible. | Serious health errors, data not accessible | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition:Simulate Network Failure (One Cable)
28 | Disconnect Network Interface. | VM remains accessible, ping is operational. | VM remained accessible, ping was successful. | Pass
29 | Monitor the cluster status and network connectivity. | Network should still function. | Network functioned properly. | Pass
30 | Check the health status for any warnings or errors. | OSDs should remain operational. | OSDs remained operational. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition:Simulate Network Failure (Two Cable)
31 | Disconnect two network cables. | Node should go down, and data should be inaccessible. | Node went down, data was inaccessible. | Pass
32 | Ensure Node is Off. | Network should be powered off. | Node was powered off. | Pass
33 | Check the health status for any warnings or errors. | Health status should show errors. | Health status showed errors. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Simulate Software Disk Failure
35 | Check zpool status and run zpool offline rpool. | The server stays online. zpool status shows the pool is DEGRADED. | The server stayed on, and the pool is DEGRADED | Pass
36 | Run zpool online rpool. | The pool status changes to repairing to start fixing itself. | The pool status changed to repairing. | Pass
37 | Check zpool status. | The pool state returns to ONLINE and is fully healthy. | The pool state returned to ONLINE and is healthy. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Simulate Physical Disk Failure
38 | Turn off the server 1nd unplug one boot SSD. | The server starts up successfully using the other SSD. | The server started up successfully. | Pass
39 | Check zpool status after the server boots. | The pool state is DEGRADED, showing it's running on one disk. | The pool state is DEGRADED. | Pass
40 | Turn off, plug the disk back in, and power on the server. | The server starts and begins the repairing process to fix the mirror. | The server started and began repairing. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Replace a Disk with a New One
41 | Take a disk offline with zpool offline and clear its label. | The pool is DEGRADED, and the disk is ready to be replaced. | The pool is DEGRADED and the disk is ready. | Pass
42 | Run zpool replace -f rpool <offline_disk_id> /dev/sdX to add the new disk | The pool status changes to repairing as it copies data to the new disk. | The pool status changed to repairing. | Pass
43 | Check zpool status after the repair is done. | The pool is ONLINE and healthy, now using the new disk. | The pool is ONLINE and healthy. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: If live migration is in progress, then we will remove the disk from the server where it is migrating.
41 | Initiate live migration of the VM from server 1 to Server B. | Initiate live migration of the VM from server 1 to Server B successfully. | Live migration started without errors. | Pass
42 | Remove the disk from server 1 while the migration is in progress. | The system should handle this gracefully. | Disk removed,migration paused with a warning message. | Pass
43 | Confirm the status of the VM after the disk removal. | It should indicate whether the migration completed or failed. | VM migration failed with an error indicating the disk is missing. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Multiple OSD Failures Exceeding Replication
44 | Force fully out the OSD | The specified OSD should be marked as OUT in the Ceph cluster. | OSDs marked as OUT successfully. | Pass
45 | Stop the ceph OSD | The OSD service should stop successfully, and the OSD should be marked as DOWN. | OSD services stopped, and OSDs marked as DOWN. | Pass
46 | Repeat steps 1 and 2 for multiple OSDs | All specified OSDs should be marked as OUT and DOWN. Affected PGs should transition to incomplete or down state. | PGs transitioned to down state, warnings: "reduced data availability." | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Ceph Monitor Failure
47 | Stop ceph monitoring and remove the data base. | Monitor service stops, and its database is permanently deleted. | Commands executed successfully; service stopped and database removed without error | Pass
48 | Check the ceph status and start the monitoring of the ceph. | Start command fails; ceph -s shows HEALTH_WARN, with 1/3 mons down and remaining two maintaining quorum. | Start command failed; ceph -s output: HEALTH_WARN, 1/3 mons down, quorum server 1, server 3. | Pass
49 | Remove ceph monitoring,edit configuration file and recreate monitoring | After cleaning configuration, creating a new monitor on server 2 should succeed, returning to HEALTH_OK. | Initial attempt failed with "address in use"; after editing config, creation was successful. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Ceph CRUSH Map Rebalance
50 | Perform a benchmark test on the specified storage pool. | A stable set of IOPS and latency metrics to use for comparison. | Baseline established: Average IOPS: 40, Average Latency: 0.389 s. | Pass
51 | Change the CRUSH rules for the storage pool. | IOPS significantly lower than 40 | Benchmark results during rebalance,Average IOPS: 40 | Fail
52 | Conduct another benchmark test on the same storage pool | latency significantly higher than 0.389 s during the rebalance. | Average Latency: 0.389 s,All PGs active+clean. | Fail
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]
Test Condition: Ceph Single-Monitor (SPOF) Failure
52 | Remove monitors server 2 and server 3 and edit the configuration file to remove stale entries. | Cluster operates with a single monitor, server 1; ceph -s shows 1 mon, GUI lists mon.server 1; health is HEALTH_WARN | Commands and edits successful; cluster reconfigured to one active monitor, confirmed by ceph -s and GUI. | Pass
54 | Execute the poweroff command on server 1. | server 1 node should shut down cleanly. | server 1 node was successfully powered off. | Pass
55 | Log into server 2 and attempt to run ceph -s and other rados commands. | All commands should hang indefinitely or time out with a connection error due to lack of monitor. | All commands hung, proving the cluster was completely non-functional. | Pass
EXPLORE | Exploratory Testing Considerations: [Additional considerations for testing in this particular test condition.]